## Initial
| Student Name: | Kieran Abelen | Tutor(s): | Dr David Weir
| Student ID: | 99162780
| Course code: | BCIT253
| Assignment: | Project Proposal
| Risk Statement |  | (Scale) | (Scale)
# | Condition | Consequence | Probability | Impact | Exposure | Mitigation | Contingency | Triggers
1 | Programs features won't work inside an html browser(lab computers) | Lose of a core feature of my program | 50% | 8 | 4 | Test my program in a browser at each step | revise a feature of the program | A feature is not working as intended inside a browser
2 | Research errors in recording information | Inconsistencies between the game and my program build. | 10% | 5 | 0.5 | Check my data with source alter research | Allow easy access to change inconsistencies | Reporting from the user that there is a inconsistency
3 | Research information is incorrect or information about something is not known | Inconsistencies between the game and my programs build. | 100% | 6 | 6 | Attempt to find this lack of information out by playing the game | Use user reported information even if they site know source | natural since the developer don’t report all there game information
4 | People are modifying there fallout game to change character stats | Some features will be outright incorrect. | 40% | 7 | 2.8 | Add some option to modify the formulas used in the builder | Try use multipliers and not static information | If the player has any mod that changes the character or his damage
5 | Not being able to finish a feature | feature from my protype has to be removed | 30% | 5 | 1.5 | Incremental approach to development | project plan scheduling of each feature | problems implementing the feature in the allocated time
6 |  |  | 0 | 0 | 0
7 |  |  | 0 | 0 | 0
8 |  |  | 0 | 0 | 0
9 |  |  | 0 | 0 | 0
10 |  |  | 0 | 0 | 0
11 |  |  | 0 | 0 | 0
12 |  |  | 0 | 0 | 0
13 |  |  | 0 | 0 | 0
14 |  |  | 0 | 0 | 0
15 |  |  | 0 | 0 | 0
16 |  |  | 0 | 0 | 0
17 |  |  | 0 | 0 | 0
18 |  |  | 0 | 0 | 0
19 |  |  | 0 | 0 | 0
20 |  |  | 0 | 0 | 0
Note on D5: Articulate the scale being used for probability inside of the parenthesis. E.g. (1-100%) Note: 100% would mean the item is no longer a risk and has become a problem.
Note on E5: Articulate the scale being used for impact inside the parenthesis. E.g. (1-10). Note: scale must have the same range as the probability.
Note on A6: Use this column as the risk identifier which, allows each risk to be uniquely identified.
Note on B6: Use this column to capture the "likely cause" of the risk. Be detailed enough so that you can start forming mitigation plans.
Note on C6: Use this column to capture the result of the risk, should it happen. If the consequences cannot be mitigated, you will have to dealt with them in a contingency plan.
Note on D6: Use this column to estimate the probability the risk will occur. Suggest using a percentage-based scale (1-99%).
Note on E6: Use this column to estimate the amount of impact or severity of the risk.
Note on F6: This column is computed as probability x impact. Once all risks have been entered, sort by this column to identify your biggest risks.
Note on G6: Use this column to document what plans the team has to prevent the risk or to reduce the impact before occurance. This may require creating a separate, more detailed plan.
Note on H6: Use this column to identify what will need to be done if the risk becomes reality. This may require creating a separate, more detailed plan.
Note on I6: Use this column to identify what would prompt you to execute the contingency plan. A trigger is usually a date or some sort of threshold.

## Midpoint
| Student Name: | Kieran Abelen | Tutor(s): | Dr David Weir
| Student ID: | 99162780
| Course code: | BCIT253
| Assignment: | Project Proposal
| Risk Statement |  | (Scale) | (Scale)
# | Condition | Consequence | Probability | Impact | Exposure | Mitigation | Contingency | Triggers
1 | Programs features won't work inside an html browser(lab computers) | Lose of a core feature of my program | 100% | 5 | 5 | Test my program in a browser at each step | revise a feature of the program | A feature is not working as intended inside a browser
2 | Research errors in recording information | Inconsistencies between the game and my program build. | 10% | 5 | 0.5 | Check my data with source alter research | Allow easy access to change inconsistencies | Reporting from the user that there is a inconsistency
3 | Research information is incorrect or information about something is not known | Inconsistencies between the game and my programs build. | 100% | 6 | 6 | Attempt to find this lack of information out by playing the game | Use user reported information even if they site know source | natural since the developer don’t report all there game information
4 | People are modifying there fallout game to change character stats | Some features will be outright incorrect. | 40% | 7 | 2.8 | Add some option to modify the formulas used in the builder | Try use multipliers and not static information | If the player has any mod that changes the character or his damage
5 | Not being able to finish a feature | feature from my protype has to be removed | 100% | 8 | 8 | Incremental approach to development | project plan scheduling of each feature | problems implementing the feature in the allocated time
6 | Risk overtime on building the javascipt | not completing the assignment | 20% | 10 | 2 | scale back features | Users will have to allow some bugs | complexity of coding
7 | overly complex and long javascript | extra time needed to modify it | 40% | 6 | 2.4 | try and reuse code | Have comment seperating similar code | lack of knowledge of the vue code and use of some of it features
8 |  |  | 0 | 0 | 0
9 |  |  | 0 | 0 | 0
10 |  |  | 0 | 0 | 0
11 |  |  | 0 | 0 | 0
12 |  |  | 0 | 0 | 0
13 |  |  | 0 | 0 | 0
14 |  |  | 0 | 0 | 0
15 |  |  | 0 | 0 | 0
16 |  |  | 0 | 0 | 0
17 |  |  | 0 | 0 | 0
18 |  |  | 0 | 0 | 0
19 |  |  | 0 | 0 | 0
20 |  |  | 0 | 0 | 0
Note on D5: Articulate the scale being used for probability inside of the parenthesis. E.g. (1-100%) Note: 100% would mean the item is no longer a risk and has become a problem.
Note on E5: Articulate the scale being used for impact inside the parenthesis. E.g. (1-10). Note: scale must have the same range as the probability.
Note on A6: Use this column as the risk identifier which, allows each risk to be uniquely identified.
Note on B6: Use this column to capture the "likely cause" of the risk. Be detailed enough so that you can start forming mitigation plans.
Note on C6: Use this column to capture the result of the risk, should it happen. If the consequences cannot be mitigated, you will have to dealt with them in a contingency plan.
Note on D6: Use this column to estimate the probability the risk will occur. Suggest using a percentage-based scale (1-99%).
Note on E6: Use this column to estimate the amount of impact or severity of the risk.
Note on F6: This column is computed as probability x impact. Once all risks have been entered, sort by this column to identify your biggest risks.
Note on G6: Use this column to document what plans the team has to prevent the risk or to reduce the impact before occurance. This may require creating a separate, more detailed plan.
Note on H6: Use this column to identify what will need to be done if the risk becomes reality. This may require creating a separate, more detailed plan.
Note on I6: Use this column to identify what would prompt you to execute the contingency plan. A trigger is usually a date or some sort of threshold.

## Final
| Student Name: | Kieran Abelen | Tutor(s): | Dr David Weir
| Student ID: | 99162780
| Course code: | BCIT253
| Assignment: | Project Proposal
| Risk Statement |  | (Scale) | (Scale)
# | Condition | Consequence | Probability | Impact | Exposure | Mitigation | Contingency | Triggers
1 | Programs features won't work inside an html browser(lab computers) | Lose of a core feature of my program | 100% | 5 | 5 | Test my program in a browser at each step | revise a feature of the program | A feature is not working as intended inside a browser
2 | Research errors in recording information | Inconsistencies between the game and my program build. | 10% | 5 | 0.5 | Check my data with source alter research | Allow easy access to change inconsistencies | Reporting from the user that there is a inconsistency
3 | Research information is incorrect or information about something is not known | Inconsistencies between the game and my programs build. | 100% | 6 | 6 | Attempt to find this lack of information out by playing the game | Use user reported information even if they site know source | natural since the developer don’t report all there game information
4 | People are modifying there fallout game to change character stats | Some features will be outright incorrect. | 40% | 7 | 2.8 | Add some option to modify the formulas used in the builder | Try use multipliers and not static information | If the player has any mod that changes the character or his damage
5 | Not being able to finish a feature | feature from my protype has to be removed | 100% | 8 | 8 | Incremental approach to development | project plan scheduling of each feature | problems implementing the feature in the allocated time
6 | Risk overtime on building the javascipt | not completing the assignment | 20% | 10 | 2 | scale back features | Users will have to allow some bugs | complexity of coding
7 | overly complex and long javascript | extra time needed to modify it | 60% | 6 | 3.6 | try and reuse code | Have comment seperating similar code | lack of knowledge of the vue code and use of some of it features
8 | Animation problems | odd placment or utility | 80% | 4 | 3.2 | google information about it to try fix | just leave it in the best state I can | HTML5 adobe animation lack of knowledge
9 | loss of buttons or naviagation | getting stuck in a screen and being forced to refresh page | 10% | 10 | 1 | make sure code properly resets to defualt settings | try have an exit on each screen | the use of a vue code v-if
10 | Hard to understand UI | the design I wanted but not acheiveing it | 80% | 2 | 1.6 | Add enough padding and margins to make things bigger | adding bootstrap is a quick fix | html design mostly being small
11 |  |  | 0 | 0 | 0
12 |  |  | 0 | 0 | 0
13 |  |  | 0 | 0 | 0
14 |  |  | 0 | 0 | 0
15 |  |  | 0 | 0 | 0
16 |  |  | 0 | 0 | 0
17 |  |  | 0 | 0 | 0
18 |  |  | 0 | 0 | 0
19 |  |  | 0 | 0 | 0
20 |  |  | 0 | 0 | 0
Note on D5: Articulate the scale being used for probability inside of the parenthesis. E.g. (1-100%) Note: 100% would mean the item is no longer a risk and has become a problem.
Note on E5: Articulate the scale being used for impact inside the parenthesis. E.g. (1-10). Note: scale must have the same range as the probability.
Note on A6: Use this column as the risk identifier which, allows each risk to be uniquely identified.
Note on B6: Use this column to capture the "likely cause" of the risk. Be detailed enough so that you can start forming mitigation plans.
Note on C6: Use this column to capture the result of the risk, should it happen. If the consequences cannot be mitigated, you will have to dealt with them in a contingency plan.
Note on D6: Use this column to estimate the probability the risk will occur. Suggest using a percentage-based scale (1-99%).
Note on E6: Use this column to estimate the amount of impact or severity of the risk.
Note on F6: This column is computed as probability x impact. Once all risks have been entered, sort by this column to identify your biggest risks.
Note on G6: Use this column to document what plans the team has to prevent the risk or to reduce the impact before occurance. This may require creating a separate, more detailed plan.
Note on H6: Use this column to identify what will need to be done if the risk becomes reality. This may require creating a separate, more detailed plan.
Note on I6: Use this column to identify what would prompt you to execute the contingency plan. A trigger is usually a date or some sort of threshold.