## Project Planner
Kieran Abelen |  | IT245 - Project Plan |  |  |  |  | Version one
Project Plan
ACTIVITY | SUB TASKS | SUB-SUB TASKS | PLNNED HOURS | ACTUAL START DATE | ACTUAL DURATION | ACTUAL COMPLETION DATE | SUBMISION DATE | TIME VARIANCE | PERCENT COMPLETE
Write Project Brief |  |  | 0.5 |  |  |  |  | -0.5
Project Plan |  |  | 0.5 |  |  |  |  | -0.5
Risk Analysis |  |  | 0.5 |  |  |  |  | -0.5
Flow chart/Navigation Map |  |  | 0.5 |  |  |  |  | -0.5
Storyboarding: | Main Menu |  | 1 |  |  |  |  | -1
| Page layout structure |  | 4 |  |  |  |  | -4
| Graphic Design |  | 2 |  |  |  |  | -2
| Video Design |  | 1 |  |  |  |  | -1
Final Submision
Create Elements | Breakfast One - overnight oats | Write recipe/Ingredients | 0.5 |  |  |  |  | -0.5
|  | Film Video/Take photos | 1 |  |  |  |  | -1
|  | Edit Video | 1 |  |  |  |  | -1
| Breakfast Two - Avocado Toast | Write recipe/Ingredients | 0.5 |  |  |  |  | -0.5
|  | Film Video/Take photos | 1 |  |  |  |  | -1
|  | Edit Video | 1 |  |  |  |  | -1
| Lunch One - Tofu Mayo | Write recipe/Ingredients | 0.5 |  |  |  |  | -0.5
|  | Film Video/Take photos | 1 |  |  |  |  | -1
|  | Edit Video | 1 |  |  |  |  | -1
| Lunh Two - Pumpkin Soup | Write recipe/Ingredients | 0.5 |  |  |  |  | -0.5
|  | Film Video/Take photos | 1 |  |  |  |  | -1
|  | Edit Video | 1 |  |  |  |  | -1
| Dinner One - Roasted Veg Salad | Write recipe/Ingredients | 0.5 |  |  |  |  | -0.5
|  | Film Video/Take photos | 1 |  |  |  |  | -1
|  | Edit Video | 1 |  |  |  |  | -1
| Dinner Two - Spaghetti Squash | Write recipe/Ingredients | 0.5 |  |  |  |  | -0.5
|  | Film Video/Take photos | 1 |  |  |  |  | -1
|  | Edit Video | 1 |  |  |  |  | -1
| Dinner Three - Bean Burger | Write recipe/Ingredients | 0.5 |  |  |  |  | -0.5
|  | Film Video/Take photos | 1 |  |  |  |  | -1
|  | Edit Video | 1 |  |  |  |  | -1
| Dinner Four - Cauliflower Pizza | Write recipe/Ingredients | 0.5 |  |  |  |  | -0.5
|  | Film Video/Take photos | 1 |  |  |  |  | -1
|  | Edit Video | 1 |  |  |  |  | 0
| Splash Page | Create animation | 1 |  |  |  |  | -1
| Main Menu |  | 1 |  |  |  |  | -1
| Shopping List | build basic page | 2 |  |  |  |  | -2
|  | Make shopping lists | 2 |  |  |  |  | -2
| About Us - build page |  | 1 |  |  |  |  | -1
| Help - build page |  | 1 |  |  |  |  | -1
| Button Building |  | 1 |  |  |  |  | -1
| Animation/transition |  | 2 |  |  |  |  | -2
Prototype | Final page layout |  | 2 |  |  |  |  | -2
| Additional transitions |  | 1 |  |  |  |  | -1
| Testing |  | 4 |  |  |  |  | -4
| Amendments |  | 10 |  |  |  |  | -10
Delivery | Final Product delivery |  | 1 |  |  |  |  | -1
|  | TOTAL PLANNED HOURS | 59 | TOTAL VARIANCE |  |  |  | -58