## Initial
| Student Name: | Kieran Abelen | Tutor(s): | Dr David Weir
| Student ID: | 99162780
| Course code: | BCIT254
| Assignment: | Project Plan
| Risk Statement |  | (Scale) | (Scale)
# | Condition | Consequence | Probability | Impact | Exposure | Mitigation | Contingency | Triggers
1 | Programs features cant be added to app | Lose of a core feature of my app | 50% | 8 | 4 | Do early prototype to explore possible loss of feature | Revise a feature of the app | Limitations inside my development tool
2 | Not being able to finish a feature | Lose of a core feature of my app | 30% | 8 | 2.4 | Incremental approach to development | Project plan scheduling of each feature | Problems implementing the feature in the allocated time
3 | Research errors in recording information | Inconsistencies between the game and my app build. | 80% | 2 | 1.6 | Check my data with source alter research | Allow easy access to change inconsistencies | Reporting from the user that there is a inconsistency
4 | Research information is incorrect or information about something is not known | Inconsistencies between the game and my app build. | 100% | 6 | 6 | Attempt to find this lack of information out by playing the game | Use user reported information even if they site know source | The developer don’t reveal all there game information
5 | Running out of time to deliver a final product | Not completing the assignment | 5% | 10 | 0.5 | Scale back features | Users will have to allow some bugs | Complexity of coding
11
12
13
14
15
16
17
18
19
20
Note on D5: Articulate the scale being used for probability inside of the parenthesis. E.g. (1-100%) Note: 100% would mean the item is no longer a risk and has become a problem.
Note on E5: Articulate the scale being used for impact inside the parenthesis. E.g. (1-10). Note: scale must have the same range as the probability.
Note on A6: Use this column as the risk identifier which, allows each risk to be uniquely identified.
Note on B6: Use this column to capture the "likely cause" of the risk. Be detailed enough so that you can start forming mitigation plans.
Note on C6: Use this column to capture the result of the risk, should it happen. If the consequences cannot be mitigated, you will have to dealt with them in a contingency plan.
Note on D6: Use this column to estimate the probability the risk will occur. Suggest using a percentage-based scale (1-99%).
Note on E6: Use this column to estimate the amount of impact or severity of the risk.
Note on F6: This column is computed as probability x impact. Once all risks have been entered, sort by this column to identify your biggest risks.
Note on G6: Use this column to document what plans the team has to prevent the risk or to reduce the impact before occurance. This may require creating a separate, more detailed plan.
Note on H6: Use this column to identify what will need to be done if the risk becomes reality. This may require creating a separate, more detailed plan.
Note on I6: Use this column to identify what would prompt you to execute the contingency plan. A trigger is usually a date or some sort of threshold.